## Summary
Architecture Review 2026-05 - Risk Register Summary
Source: docs/arc42/review-2026-05/01_architecture_review_overview.en.md (Section 3: Priority items for go-live)
By Project
Project | CRITICAL | HIGH | Total
aihub-core | 9 | 21 | 30
aihub-bmd | 1 | 10 | 11
aihub-ctc | 4 | 14 | 18
aihub-demoscope | 5 | 9 | 14
aihub-wpe | 2 | 9 | 11
aihub-fmh | 5 | 7 | 12
TOTAL | 26 | 70 | 96
Legend
CRITICAL | Blocks go-live: data loss / security breach / compliance violation if not addressed
HIGH | Significant impact on scale/reliability/compliance; address before expanding customer base
Note: Proposed ADR codes (ADR-NEW-xxx) map to docs/arc42/review-2026-05/05_proposed_adrs/.
Severity assumes the scenario: new customer onboarding with mid-to-high compliance requirement (Swiss regulated industry).

## Risk Register
ID | Project | Title | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
CORE-01 | aihub-core | Sovereignty path not yet decided | Swiss data sovereignty (ADR 2026_02_24) is violated across customers (Azure OpenAI / Foundry / AI Search). The platform has no decided path reconciling marketing claim with reality. | CRITICAL | Sovereignty & Compliance | Choose Option A (self-hosted local LLM) / B (hybrid with updated ADR allowing Azure-EU) / C (per-customer sovereignty tier); update ADR 2026_02_24. | ADR-000; ADR-016; ADR-017 | Cross-cutting: all customer deployments inherit this decision.
CORE-02 | aihub-core | UsageLimits enforcement incomplete | UsageLimits wired only at agent endpoints + OpenAI route. No 4-layer enforcement, no pre-flight estimation, no hard cap -> LLM cost runaway risk. | CRITICAL | Cost / Security | Extend to 4-layer enforcement (per-user/tenant/model/global) across all routes; pre-flight cost estimation; hard cap with circuit breaker. | ADR-012; ADR-023
CORE-03 | aihub-core | Multi-tenant data layer not isolated | Tenant exists only at Keycloak layer. MongoDB entities lack tenant_id, NATS subjects/Milvus/Valkey/Neo4j not namespaced per-tenant. Isolation depends entirely on AccessChecker. | CRITICAL | Multi-Tenancy | Add required tenant_id field; per-tenant Milvus collection; NATS subject namespace aihub.tenant.{id}.*; Valkey key prefix; auto-filter repository wrapper. | ADR-002; ADR-047 | Commercial blocker for any multi-subsidiary / data-isolated deployment.
CORE-04 | aihub-core | Document ACL not inherited into Milvus | ACL from source systems (Jira/SharePoint/Confluence/SMB) is not inherited into Milvus metadata; retrieval does not filter by user -> cross-user data leak via RAG. | CRITICAL | Security | ACL metadata field in Milvus + retrieval-time filter by user_groups. | ADR-020
CORE-05 | aihub-core | MCP tool args bypass Presidio | MCP tool execution sends args directly, not via LiteLLM proxy; Presidio PII guard bypassed 100% -> PII leaks to external tool servers. | CRITICAL | Security | Implement SecureMCPExecutor with Presidio sanitization + tool authorization. | ADR-019
CORE-06 | aihub-core | AuditLogEntity missing | No dedicated AuditLogEntity in the codebase. Violates GDPR Art.30, ISO 27001 A.12.4, SOC2 CC7.2. Docs falsely claim immutable audit logs. | CRITICAL | Security & Compliance | Write-once entity with retention policy + tamper-evident hash chain. | ADR-011
CORE-07 | aihub-core | GDPR right-to-erasure unimplementable | No cascade user/tenant DELETE endpoint; data spread across Mongo/Milvus/Neo4j/Valkey/SeaweedFS with no deletion path. Erasure requests cannot be fulfilled. | CRITICAL | Compliance | Implement cascade DELETE endpoint for user/tenant across all stores; document compliance procedure. | ADR-026
CORE-08 | aihub-core | No DLQ for JetStream poison messages | Poison messages have no dead-letter queue; a bad event causes consumer crash loop blocking downstream processing. | CRITICAL | Reliability & Data Integrity | DLQ subject aihub.dlq.* with max-retry policy + alerting.
CORE-09 | aihub-core | No circuit breaker for external deps | Calls to LiteLLM/Keycloak/Milvus have no breaker; external outages cascade across the platform with no degraded mode. | CRITICAL | Reliability & Data Integrity | pybreaker per LiteLLM/Keycloak/Milvus with threshold + half-open recovery. | ADR-034; ADR-036
CORE-10 | aihub-core | No HA architecture | Every stateful service is single-instance (PostgreSQL/NATS/Valkey/Milvus/Keycloak/etcd) -> SPOF. | HIGH | Performance & Scalability | HA roadmap per service: Postgres streaming replication, NATS 3-node cluster, Valkey Sentinel, Milvus cluster mode, Keycloak Infinispan, etcd 3-node.
CORE-11 | aihub-core | No DB migration framework | Schemas created implicitly by Pydantic + MongoEngine at startup. Core upgrade may silently drop fields; no rollback or migration history. | HIGH | Reliability & Data Integrity | Versioned migration framework (Alembic-like) + metadata collection tracking applied migrations. | ADR-003 | Blocks safe SDK upgrades (see CTC-18).
CORE-12 | aihub-core | False docs claims | CLAUDE.md / GDPR docs claim Presidio integration, GDPR right-to-erasure, and immutable audit logs that do not exist in code. | HIGH | Documentation / Compliance | Remove false claims from CLAUDE.md + GDPR docs; sync with reality; add doc-code drift detection CI. | ADR-017
CORE-13 | aihub-core | Presidio DE-only multilingual gap | Presidio analyzer hardcodes 'de' across 10 LiteLLM config files. Swiss FR/IT/EN data not PII-masked before reaching the LLM. | HIGH | Security | Per-language Presidio routing (DE/FR/IT/EN) + Swiss custom recognizers (AHV, CHE-UID, +41 phone). | ADR-018
CORE-14 | aihub-core | No mTLS service-to-service | NATS token-only auth; Mongo/Redis use connection strings; internal traffic not mutually authenticated -> MITM risk inside cluster. | HIGH | Security | mTLS for NATS/Mongo/Redis with automated cert rotation (cert-manager / Vault).
CORE-15 | aihub-core | No supply chain security (SBOM/signing/scan) | No SBOM, image signing, or vulnerability scanning -> unknown CVEs in images, supply-chain attack risk. | HIGH | Security | syft (SBOM) + cosign (image signing) + trivy (vuln scan) in CI. | ADR-029
CORE-16 | aihub-core | No API rate limiting | API has no per-user / per-tenant rate limit -> DoS risk and cost runaway if requests reach LLM endpoints. | HIGH | Security | Redis-backed rate limiter middleware per user + per tenant.
CORE-17 | aihub-core | Milvus single-node memory wall | Single-node Milvus, HNSW memory wall (122 GB RAM for 10M x 3072d x 4B). | HIGH | Performance & Scalability | Milvus cluster mode + DISKANN benchmark for disk-backed index. | ADR-015
CORE-18 | aihub-core | No formal alerting infrastructure | Only Slack notification on Ansible Pull failure; no AlertManager, no on-call routing, no per-service severity rules. | HIGH | Observability | Prometheus AlertManager + PagerDuty/OpsGenie on-call routing + per-service severity rules. | ADR-032
CORE-19 | aihub-core | No business metrics + formal SLI/SLO | No business metrics (agent_runs, HITL escalations, RAG latency); no formal SLI/SLO documented per service. | HIGH | Observability | Business metrics export; formal SLI/SLO documented per service. | ADR-010; ADR-033
CORE-20 | aihub-core | No K8s migration path (partially addressed) | Single-server ceiling for Gen 1/Gen 2. aihub-k8s (Gen 3) exists with Terraform + Helm but no prod customer migrated; charts do NOT pin a core version. | HIGH | Operational Excellence | Adopt Gen 3 via ADR; chart-level core version pin policy; migrate >=1 prod customer; cluster-mode Milvus + HPA validation; document Gen 1 -> Gen 3 migration. | ADR-040
CORE-21 | aihub-core | No load test baseline | No load test suite or baseline numbers per critical path. | HIGH | Performance / Quality | Load test suite (k6/Locust) in CI with baseline numbers per critical path. | ADR-046
CORE-22 | aihub-core | Connector framework missing | Every customer rebuilds source connectors (O(NxM) onboarding cost). | HIGH | SDK / Operational | BaseSourceConnector framework + built-in connectors (SMB, S3, SharePoint, Confluence, Jira, GitHub, Notion, Drive, Box, Salesforce, IMAP). | ADR-004
CORE-23 | aihub-core | Code RAG semantic-only (missing structural chunks) | Code RAG uses semantic chunking only, missing structural / AST-aware chunks and symbol indexing. | HIGH | Performance / RAG | tree-sitter AST chunking + code-specific embedding (CodeBERT/UniXcoder) + hybrid index (vector + symbol + Neo4j call-graph). | ADR-044
CORE-24 | aihub-core | Open-source dependency lock-in | Parser/embedding/reranker/vector store/PII detector/speech not abstracted -> lock-in to specific OSS components. | HIGH | Sustainability / Architecture | Hexagonal Ports & Adapters for 6 layers (DocumentParser/EmbeddingProvider/Reranker/VectorStore/PIIDetector/SpeechProcessor) + contract tests. | ADR-024; ADR-043
CORE-25 | aihub-core | Workflow architecture Process vs Agentic undecided | packages/process is dead code; strategic direction (hybrid vs deprecate) undecided. Docs still advertise process engine. | HIGH | Architecture | Option A (activate hybrid Process+Agentic with routing criteria) or Option B (deprecate process cleanly + migration guide). | ADR-013
CORE-26 | aihub-core | No run / AITL timeout | No explicit timeout per agent run; recursive AITL escalation has no depth hardcap. | HIGH | Reliability & Data Integrity | Explicit timeout per agent run + MAX_AITL_DEPTH = 5 hardcap for recursive escalation. | ADR-022
CORE-27 | aihub-core | Container resource limits missing in production | No deploy.resources.limits in docker-compose -> 1 container OOM can crash host. | HIGH | Operational / Performance | Explicit deploy.resources.limits (CPU/memory) per service; profile-based sizing.
CORE-28 | aihub-core | Backup encryption at rest not verified | Restic backup encryption for off-host backup not verified; key management undocumented. | HIGH | Reliability & Data Integrity | Verify Restic encryption enabled for off-host backup; document encryption key management + rotation procedure. | ADR-030
CORE-29 | aihub-core | Keycloak signing key rotation procedure missing | No JWT signing key rotation procedure -> compromised key = unlimited token forgery. | HIGH | Security | Document JWT signing key rotation (every 6 months); automation script; audit log. | ADR-005
CORE-30 | aihub-core | Image vulnerability remediation SLA missing | No SLA for remediating CVEs in container images (separate from scanning). | HIGH | Security | SLA for critical CVE (7 days), high (30 days), medium (90 days); track in dashboard. | ADR-029
BMD-01 | aihub-bmd | Backup destination on the same VM | FATAL: backup stored on same SeaweedFS / same VM. VM dies = total data loss. Violates 3-2-1 rule. | CRITICAL | Reliability & Data Integrity | Emergency cron sync to Swiss-sovereign off-site (Infomaniak CH / Exoscale CH / Hetzner); long-term migrate to Gen 2 (Restic->Swift). | ADR-030; ADR-031
BMD-02 | aihub-bmd | Azure OpenAI (Sweden) sovereignty violation | LiteLLM config 100% Azure OpenAI (Sweden region) -> violates core sovereignty ADR 2026_02_24. | HIGH | Sovereignty & Compliance | Tied to core sovereignty path decision (Option A/B/C); ADR documenting trade-off or migration plan. | ADR-000 | Severity depends on customer compliance contract.
BMD-03 | aihub-bmd | Test coverage near-zero | Only 59 lines / 1 utility (test_snk_enrichment.py); agents and pipelines untested. | HIGH | Quality Assurance | Baseline test plan (smoke tests per agent/pipeline); integration test with staging data; coverage threshold 60% for new code.
BMD-04 | aihub-bmd | SDK drift 11 minor versions | v0.279.2 vs core v0.290.4. Security patches do not propagate. | HIGH | SDK Versioning | SDK upgrade plan with security delta audit; extract reusable patterns to core; CI gate blocking drift > N versions. Near-latest pin -> lowest-risk upgrade; do first as quick win. | ADR-001; ADR-009
BMD-05 | aihub-bmd | Cohere reranking US/Canada vendor | Reranker uses Cohere (US/Canada) -> vendor + sovereignty concern. | HIGH | Sovereignty & Compliance | ADR documenting sovereignty trade-off or migrate to sovereign alternative (local BGE, local Jina). | ADR-000
BMD-06 | aihub-bmd | Storage multiplier 3.9x | ~3.9x storage multiplier (1 TB source -> 5.1 TB). 1.9 TB disk insufficient for 2+ customers. | HIGH | Performance & Scalability | Data partitioning strategy (sharding / time-based / customer-based / cold storage); ADR documenting strategy.
BMD-07 | aihub-bmd | Hardcoded customer config | SNK_ANCHOR, BASE_PATH (SMB share /mnt/smb_bmd/...) hardcoded in pipeline. | HIGH | Operational / Config | Pydantic Settings from env per deployment; documented config matrix. | ADR-004
BMD-08 | aihub-bmd | Weak model malformed JSON breaks workflow | Weak model can emit malformed JSON that breaks the workflow; no structured-output guard. | HIGH | Reliability / Quality | Structured output / JSON mode (response_format) + Pydantic validation + fallback chain weak->strong model + golden test suite in CI.
BMD-09 | aihub-bmd | No resource limits in docker-compose | No CPU/memory limits per service. | HIGH | Operational / Performance | Explicit CPU/memory limits per service; profile-based sizing.
BMD-10 | aihub-bmd | Internal import violation | pipelines/snk_enrichment.py:2 imports core internal module (swiss_ai_hub.core.persistence.rag.vectors.node_metadata). | HIGH | SDK Versioning | Fix import via core public API (__init__.py); lint rule blocking internal imports. | ADR-038; ADR-006
BMD-11 | aihub-bmd | No own arc42 + ADRs | No architecture documentation or decision records; design lives only in code. | HIGH | Documentation | arc42 12-chapter skeleton + C4 L1/L2 + 10 ADRs (sovereignty, partitioning, SMB path, SNK enrichment, regex utils, Cohere choice, etc.).
CTC-01 | aihub-ctc | Backup destination on the same Azure VM | FATAL: backup on same Azure VM. VM dies = total loss. | CRITICAL | Reliability & Data Integrity | Tier 1 emergency cron sync to Swiss off-site; plan migration to Gen 2 with cross-region replication. | ADR-030; ADR-031
CTC-02 | aihub-ctc | Azure AI Foundry + Azure DI sovereignty violation | LiteLLM config 100% Azure AI Foundry (SUI+SWE) + Azure Document Intelligence -> violates core sovereignty ADR. | CRITICAL | Sovereignty & Compliance | Standardize on core stack (MinerU + LiteLLM gateway); migration roadmap DI -> MinerU, Foundry -> vLLM/Swiss LLM Cloud via LiteLLM. | ADR-000; ADR-016
CTC-03 | aihub-ctc | Per-user data access control missing | 3 manifestations, same root cause: service-account shared keys, no data-layer isolation, no ACL inheritance. Cross-user data leak. GDPR Art.32/25. | CRITICAL | Security | Per-user OAuth delegated permissions for Jira/SharePoint/Confluence; data-layer isolation (per-tenant Milvus, per-user ACL filter); ACL inheritance into Milvus; documented access matrix; forensic audit log. | ADR-020; ADR-021; ADR-002
CTC-04 | aihub-ctc | Test coverage minimal | Only 3 files / 788 lines in log_analysis_agent; chat / jira_issue / retrieval_orchestrator agents + 6 pipelines + custom API + lib/common untested. | HIGH | Quality Assurance | Extend log_analysis_agent style coverage to all components; smoke tests per agent; integration test with staging Jira/Confluence/SharePoint; coverage threshold 60%.
CTC-05 | aihub-ctc | SDK drift 16 minor versions | v0.274.3 vs core v0.290.4. | HIGH | SDK Versioning | SDK upgrade with security delta audit; standardize uv workflow; deprecate poetry.lock; CI gate blocking drift. | ADR-001; ADR-009
CTC-06 | aihub-ctc | SharePoint over-permissioned Sites.Read.All | Azure AD app-only Sites.Read.All tenant-wide -> excessive scope. | HIGH | Security | Scoped permission Sites.Selected per site; documented access matrix per site. | ADR-021 | Sub-aspect of CTC-03.
CTC-07 | aihub-ctc | Hardcoded Jira config (URL/IDs) | JIRA_URL, Service Desk ID, Request Type ID, Project hardcoded. | HIGH | Operational / Config | Pydantic Settings from env per deployment. | ADR-004
CTC-08 | aihub-ctc | Naming camouflage (gpt-oss-120b -> azure/gpt-5-nano) | Model alias hides that an Azure model backs an open-source-looking name. | HIGH | Sovereignty / Transparency | Transparent naming convention (e.g., azure-eu/gpt-5-nano); ADR documenting trade-off. | ADR-000
CTC-09 | aihub-ctc | Jira webhook not idempotent | JiraWebhookController: same event delivered 2x = 2 agent runs. | HIGH | Reliability & Data Integrity | Idempotency key from webhook event ID; Redis lock pattern.
CTC-10 | aihub-ctc | Custom API not yet contributed to core | Jira webhook + Support Desk endpoints live only in customer repo. | HIGH | SDK / Architecture | Extract Jira webhook + Support Desk endpoint to core as extension points; ADR decision on when to extract.
CTC-11 | aihub-ctc | External services cascade risk | Jira/Confluence/SharePoint/Azure outage cascades with no breaker/fallback. | HIGH | Reliability & Data Integrity | Circuit breaker per source; cached fallback for read paths; documented DR plan. | ADR-034
CTC-12 | aihub-ctc | Azure stack triple redundancy | Azure DI + Foundry + core MinerU+LiteLLM all present -> redundant Azure dependency. | HIGH | Sovereignty / Cost | Standardize on core stack; ADR documenting Azure-specific justification; migration roadmap. | ADR-039
CTC-13 | aihub-ctc | Azure AD B2C vendor lock-in | Identity federated via Azure AD B2C instead of pure Keycloak. | HIGH | Security / Architecture | ADR documenting trade-off; evaluate pure Keycloak federation alternative.
CTC-14 | aihub-ctc | Internal import violation (lib/common/types) | lib/common/types/RetrievalAgentInTheLoop.py:1-4 imports non-public core module path. | HIGH | SDK Versioning | Fix import via core public API; lint rule blocking. | ADR-038; ADR-006
CTC-15 | aihub-ctc | Dual lock files | poetry.lock (84KB) + uv.lock coexist -> confusion. | HIGH | SDK / Operational | Migrate to uv-only workflow; deprecate poetry.lock; standard uv commands. | ADR-001
CTC-16 | aihub-ctc | No own arc42 + ADRs | No architecture docs or decision records. | HIGH | Documentation | arc42 12 chapters + C4 L1/L2 + 13 ADRs (Azure Foundry, DI vs MinerU, naming camouflage, service account, AD B2C, etc.).
CTC-17 | aihub-ctc | Deep-import violations in ChatAgent.py | ChatAgent.py reaches swiss_ai_hub.core.generative_ai.{chat_history,guards} and core.i18n.locale_handler, bypassing public API. | HIGH | SDK Versioning | Refactor to import via public interface after promoting needed symbols; add ruff/lint rule blocking deep imports; CI gate. | ADR-038
CTC-18 | aihub-ctc | MongoDB tenant-entry schema migration required | Tenant-entry schema changed between pinned and current core -> migration required before SDK upgrade. Biggest upgrade risk for CTC. | CRITICAL | Reliability / SDK | Build on DB migration framework (ADR-003); author forward + rollback migration; reconcile tenant docs vs Keycloak source of truth; dry-run on restored copy in maintenance window. | ADR-045; ADR-003
DEMO-01 | aihub-demoscope | SDK drift 44 minor versions | v0.246.4* vs core v0.290.4 (4.5+ months behind). *SDK pin not present in pyproject.toml. | CRITICAL | SDK Versioning | Confirm actual SDK pin via deploy manifests/CI; SDK upgrade plan with security delta audit; CI gate blocking drift; coordinate breaking-change migration. | ADR-001; ADR-009
DEMO-02 | aihub-demoscope | Backup destination on the same VM | MinIO on same host as Milvus / Mongo. | CRITICAL | Reliability & Data Integrity | Emergency cron sync to Swiss off-site; replace ad-hoc backup_updater_script.py with official milvus-backup to off-host bucket; documented restore drill. | ADR-030; ADR-031
DEMO-03 | aihub-demoscope | Pulumi mentioned but IaC code not committed | README claims Pulumi but no .iac/ folder in repo -> deployment irreproducible. | CRITICAL | Operational Excellence | Commit the actual Pulumi code or remove README sections; pick one IaC approach; document the real deployment process.
DEMO-04 | aihub-demoscope | Test coverage ZERO | No test_*.py, no .feature files (2 agents + 1 pipeline). | HIGH | Quality Assurance | Baseline test plan (smoke tests per agent + pipeline); BDD .feature for hash-partitioned questions flow; integration test against staging Milvus.
DEMO-05 | aihub-demoscope | Manual production migration via SSH + screen + scp | Migration done by scp + screen on the VM; progress tracked in migration_log.json on VM. | HIGH | Operational Excellence | Replace with Dagster job or k8s Job; track migration progress in DB, not a file on the VM.
DEMO-06 | aihub-demoscope | Hash-partitioned Milvus design hardcoded in 3 places | Hash partition logic duplicated across agent + pipeline + migration script -> drift risk. | HIGH | Reliability / Architecture | Single source of truth (partition_utils.py); CI test asserting agent + pipeline + migration use the same hash function.
DEMO-07 | aihub-demoscope | 4 agent variants deployed | persona / multi_personas x public / private -> large operational surface. | HIGH | Operational Excellence | Document public/private split rationale in ADR; verify 4 instances run same code or merge into 1 binary with config flag.
DEMO-08 | aihub-demoscope | Stack divergence from core (MongoDB + Redis) | Uses MongoDB + Redis instead of FerretDB + Valkey. | HIGH | Architecture | ADR documenting why diverged; migration plan or accept divergence; check Mongo-specific features blocking migration.
DEMO-09 | aihub-demoscope | Phoenix v10.0.4 + LiteLLM v1.77.7 (pre-Langfuse) | Pre-Langfuse observability (ADR 2026_02_10) and older LiteLLM with missing security patches. | HIGH | Observability / Security | Plan migration Phoenix -> Langfuse (ADR 2026_02_10); bump LiteLLM to current stable (v1.79+).
DEMO-10 | aihub-demoscope | Mixed sovereignty | Azure OpenAI SUI + local vLLM (Gemma-3, gte-Qwen2, bge-reranker). | HIGH | Sovereignty & Compliance | Document partial-sovereignty position in ADR; clarify which workloads route to Azure SUI vs local vLLM; tied to core sovereignty decision. | ADR-000
DEMO-11 | aihub-demoscope | No own arc42 + ADRs | No architecture docs or decision records. | HIGH | Documentation | arc42 12 chapters + C4 L1/L2 + ADRs (stack divergence, hash partitioning, 4-variant split, sovereignty position, MinIO same-VM backup, hashed persona_id).
DEMO-12 | aihub-demoscope | Agent crashes on start when upgrading the SDK | Pin is very old; agent crashes on start when upgrading SDK. | CRITICAL | SDK Versioning | Reproduce crash on staging copy; decide remediate-in-place vs rebuild on current core generation; sequence after a verified backup. | ADR-001
DEMO-13 | aihub-demoscope | No backup/restore actually built | Only ad-hoc backup_updater_script.py; no token/key renewal management. Customer formally accepts responsibility. | CRITICAL | Reliability & Data Integrity | Record as customer-accepted risk (RACI) with explicit sign-off and documented data-loss exposure; provide minimal backup + key/token renewal runbook. | ADR-030
DEMO-14 | aihub-demoscope | Vectors held in-memory | Works only because the box has 200 GB RAM -> cost wall as data grows. | HIGH | Performance & Scalability | Plan move to disk-backed Milvus / DISKANN before data growth; add capacity projection; run RAG/vector-design gate. | ADR-044; ADR-046
WPE-01 | aihub-wpe | TLS private key committed to git | wpe.ai-agents.ch+1-key.pem tracked alongside production cert; only .env is gitignored. | CRITICAL | Security | Rotate cert + key immediately (Let's Encrypt re-issue via Traefik); add *.pem, *-key.pem, secrets/ to .gitignore; rewrite git history (BFG / git filter-repo); audit who pulled the repo. | ADR-041
WPE-02 | aihub-wpe | Manual VM deployment via copy-paste | README: cp docker-compose.latest.yml /opt/docker/config/bbv/. No rollback, audit trail, or drift detection. | CRITICAL | Operational Excellence | Add minimum reproducible deploy: bash script + checksums, or migrate to Gen 2 (Ansible Pull) / Gen 3 (aihub-k8s).
WPE-03 | aihub-wpe | LLM region not in repo | Azure OpenAI base URL env-var only -> sovereignty unverified. | HIGH | Sovereignty & Compliance | Commit non-secret litellm-region.md or .env.example stating Azure region; ADR aligning with core sovereignty path. | ADR-000
WPE-04 | aihub-wpe | SDK drift 35 minor versions | v0.255.6 vs core v0.290.4. | HIGH | SDK Versioning | Bump CORE_VERSION in .env.prod with security delta review; CI gate blocking drift; pin via tag, not latest fallback. | ADR-001
WPE-05 | aihub-wpe | ${CORE_VERSION:-latest} fallback to latest | If env var missing, falls back to latest image -> non-reproducible builds. | HIGH | Operational Excellence | Remove :-latest default - force explicit pinning; deployment must fail-fast if CORE_VERSION is unset. | ADR-040
WPE-06 | aihub-wpe | VOLUME_ROOT defaults to local relative dir | VOLUME_ROOT:-./.docker-volumes defaults to a local relative dir in production. | HIGH | Reliability / Operational | Force VOLUME_ROOT to be set (no :- fallback); document production volume root + snapshot strategy.
WPE-07 | aihub-wpe | Off-site backup not in repo | No evidence of Restic / Swift / cross-region sync. | HIGH | Reliability & Data Integrity | Add backup config to repo (cron + Restic to Swiss off-site); follow 3-2-1 rule; document RTO/RPO. | ADR-030; ADR-031
WPE-08 | aihub-wpe | No own arc42 + ADRs | Deployment-only repo with no design docs. | HIGH | Documentation | Minimal arc42 (context + deployment + crosscutting); ADRs for manual VM choice, identity provider, LLM region, sovereignty position.
WPE-09 | aihub-wpe | No tests of any kind | Deployment-only repo with no smoke/health validation scripts. | HIGH | Quality Assurance | Add post-deploy smoke test (curl health endpoints, OAuth round-trip, LiteLLM ping, OpenWebUI login); fail fast on broken deploy.
WPE-10 | aihub-wpe | SigNoz Cloud EU region for OTEL | Observability data leaves tenant infra; sovereignty unclear (same caveat as core). | HIGH | Observability / Sovereignty | Inherit core ADR on SigNoz region once written; document the choice locally in WPE README.
WPE-11 | aihub-wpe | Customer reports poor platform performance | Root cause unknown, customer unresponsive; investigation blocked pending customer data. | HIGH | Performance & Scalability | Review Langfuse/OTEL traces + run load-test baseline (Locust) against config/hardware replica to locate bottleneck. | ADR-046 | BLOCKED pending customer input/data.
FMH-01 | aihub-fmh | SDK drift 104 minor versions | v0.186.0 vs core v0.290.4 - largest drift of all customers (10+ months of patches missed). | CRITICAL | SDK Versioning | Multi-step SDK upgrade plan with security delta audit; incremental upgrades v0.186 -> v0.220 -> v0.260 -> v0.290; CI gate blocking drift. | ADR-001; ADR-009
FMH-02 | aihub-fmh | LlamaIndex monkey-patch for GPT-5 | lib/common/register_openai_models.py modifies third-party globals at import time; behaviour depends on import order; drops on SDK upgrade. | CRITICAL | Architecture / Reliability | Replace with first-class core support (PR to aihub-core adding GPT-5 model registry); document workaround in ADR until removed.
FMH-03 | aihub-fmh | Azure AI Search instead of Milvus | Stack divergence from core; vendor lock-in + double inference cost (AI Search query + LLM call). | CRITICAL | Architecture / Sovereignty | ADR justifying Azure AI Search vs core Milvus; migration plan to Milvus or formal acceptance of divergence with cost analysis. | ADR-039
FMH-04 | aihub-fmh | Backup status not in repo | Pulumi stores/ deploys infra but no backup workload visible. | CRITICAL | Reliability & Data Integrity | Verify Azure backup policy on Storage Account + CosmosDB/Mongo; cross-region replication for TARDOC/TARMED data; documented restore drill. | ADR-030; ADR-031
FMH-05 | aihub-fmh | Stack divergence (MongoDB + Redis + Phoenix) | Pre-Langfuse stack, same as Demoscope. | HIGH | Observability / Architecture | Plan migration Phoenix -> Langfuse (ADR 2026_02_10); plan MongoDB -> FerretDB; tied to SDK upgrade.
FMH-06 | aihub-fmh | Minimal test coverage | 5 test_*.py + 5 BDD .feature for 3 agents + 2 pipelines. | HIGH | Quality Assurance | Coverage threshold 60% for new code; BDD features for 3-agent routing flow; integration test against TARMED test fixtures.
FMH-07 | aihub-fmh | Azure OpenAI Switzerland North + Azure AD vendor lock-in | Similar to CTC; Azure across multiple layers. | HIGH | Sovereignty / Architecture | ADR documenting Azure choice rationale (TARDOC/TARMED is Swiss-only data, so Switzerland North is defensible); evaluate Keycloak federation alternative. | ADR-000
FMH-08 | aihub-fmh | Bot uses MS Bot Framework + dev tunnel | dev/prod parity risk; prod may depend on devtunnel workflow. | HIGH | Operational Excellence | Document MS Teams integration deployment path; remove bot_emulator references from prod docs; ensure prod doesn't depend on devtunnel.
FMH-09 | aihub-fmh | Pulumi state in Azure storage account | Single-cloud dependency; if Azure account compromised, deployment is unrecoverable. | HIGH | Operational / Reliability | Document Pulumi state account name/region in repo (not just credentials); plan state backup.
FMH-10 | aihub-fmh | No own arc42 + ADRs | Has good IaC + evaluation framework but no design docs. | HIGH | Documentation | arc42 12 chapters + C4 L1/L2 + ADRs (Azure AI Search vs Milvus, GPT-5 monkey-patch, 3-agent routing, TARDOC/TARMED ingestion, MS Bot Framework choice).
FMH-11 | aihub-fmh | Hardcoded handbook namespace | handbook_02_2026 hardcoded in pipeline __init__.py. | HIGH | Operational / Config | Pydantic Settings from env; allow multiple snapshots in parallel; document versioning convention (handbook_MM_YYYY). | ADR-004
FMH-12 | aihub-fmh | Customer dissatisfied with answer quality | Structured TARDOC/TARMED data not ingested with a designed vector schema; no RAG testing/eval strategy (evaluation/ framework exists but unused). | CRITICAL | Performance / RAG | Run RAG/vector-design gate (field-aware chunking + metadata schema); wire eval harness on existing evaluation/ framework + Langfuse datasets; baseline then tune; tie to AI-Search-vs-Milvus decision. | ADR-044; ADR-039