## Summary
Architecture Review 2026-05 - Major Risks Summary
Source: docs/arc42/review-2026-05/ (Overview Section 3 + C4 deployment_generations.md + c4/igs.md)
By Scope (Projects + Deployment Generations)
Scope | Type | CRITICAL | HIGH | Total
aihub-core | Platform | 9 | 29 | 38
aihub-bmd | Customer | 1 | 10 | 11
aihub-ctc | Customer | 4 | 14 | 18
aihub-demoscope | Customer | 5 | 9 | 14
aihub-wpe | Customer | 2 | 10 | 12
aihub-fmh | Customer | 5 | 7 | 12
aihub-igs | Customer (Gen 2 pilot) | 1 | 7 | 8
Gen 1 (Manual VM) | Deployment | 1 | 6 | 7
Gen 2 (Ansible Pull) | Deployment | 0 | 9 | 9
Gen 3 (Kubernetes) | Deployment | 2 | 9 | 11
TOTAL |  | 30 | 110 | 140
Legend
CRITICAL | Blocks go-live: data loss / security breach / compliance violation if not addressed
HIGH | Significant impact on scale/reliability/compliance; address before expanding customer base
aihub-igs = Gen 2 pre-production pilot (deploy-only); see c4/igs.md + Overview §3.7.

## aihub-core
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
CORE-01 | Sovereignty path not yet decided | We promise Swiss data stays in Switzerland, but customer systems send data to Microsoft Azure abroad. We must pick an official policy before a regulated client audits us. | Swiss data sovereignty (ADR 2026_02_24) is violated across customers (Azure OpenAI / Foundry / AI Search). The platform has no decided path reconciling marketing claim with reality. | CRITICAL | Sovereignty & Compliance | Choose Option A (self-hosted local LLM) / B (hybrid with updated ADR allowing Azure-EU) / C (per-customer sovereignty tier); update ADR 2026_02_24. | ADR-000; ADR-016; ADR-017 | Cross-cutting: all customer deployments inherit this decision.
CORE-02 | UsageLimits enforcement incomplete | There is no hard spending limit on AI usage, so a runaway or abusive user could run up a large, uncapped bill. | UsageLimits wired only at agent endpoints + OpenAI route. No 4-layer enforcement, no pre-flight estimation, no hard cap -> LLM cost runaway risk. | CRITICAL | Cost / Security | Extend to 4-layer enforcement (per-user/tenant/model/global) across all routes; pre-flight cost estimation; hard cap with circuit breaker. | ADR-012; ADR-023
CORE-03 | Multi-tenant data layer not isolated | Different customers'/departments' data is not truly separated in the database; one wrong setting could expose one tenant's data to another. | Tenant exists only at Keycloak layer. MongoDB entities lack tenant_id, NATS subjects/Milvus/Valkey/Neo4j not namespaced per-tenant. Isolation depends entirely on AccessChecker. | CRITICAL | Multi-Tenancy | Add required tenant_id field; per-tenant Milvus collection; NATS subject namespace aihub.tenant.{id}.*; Valkey key prefix; auto-filter repository wrapper. | ADR-002; ADR-047 | Commercial blocker for any multi-subsidiary / data-isolated deployment.
CORE-04 | Document ACL not inherited into Milvus | Search results don't respect document permissions, so a user could see content from files they shouldn't have access to. | ACL from source systems (Jira/SharePoint/Confluence/SMB) is not inherited into Milvus metadata; retrieval does not filter by user -> cross-user data leak via RAG. | CRITICAL | Security | ACL metadata field in Milvus + retrieval-time filter by user_groups. | ADR-020
CORE-05 | MCP tool args bypass Presidio | When AI tools call external services, personal data is sent without the privacy filter, risking a data-protection breach. | MCP tool execution sends args directly, not via LiteLLM proxy; Presidio PII guard bypassed 100% -> PII leaks to external tool servers. | CRITICAL | Security | Implement SecureMCPExecutor with Presidio sanitization + tool authorization. | ADR-019
CORE-06 | AuditLogEntity missing | We have no tamper-proof record of who did what, which fails GDPR / ISO / SOC2 audits. | No dedicated AuditLogEntity in the codebase. Violates GDPR Art.30, ISO 27001 A.12.4, SOC2 CC7.2. Docs falsely claim immutable audit logs. | CRITICAL | Security & Compliance | Write-once entity with retention policy + tamper-evident hash chain. | ADR-011
CORE-07 | GDPR right-to-erasure unimplementable | We cannot fully delete a user's data on request, so we can't honour a legal 'right to be forgotten' demand. | No cascade user/tenant DELETE endpoint; data spread across Mongo/Milvus/Neo4j/Valkey/SeaweedFS with no deletion path. Erasure requests cannot be fulfilled. | CRITICAL | Compliance | Implement cascade DELETE endpoint for user/tenant across all stores; document compliance procedure. | ADR-026
CORE-08 | No DLQ for JetStream poison messages | A single bad message can jam the system and stall processing for everyone until someone steps in. | Poison messages have no dead-letter queue; a bad event causes consumer crash loop blocking downstream processing. | CRITICAL | Reliability & Data Integrity | DLQ subject aihub.dlq.* with max-retry policy + alerting.
CORE-09 | No circuit breaker for external deps | If one external service (e.g. the AI provider) goes down, it can drag the whole platform down with it. | Calls to LiteLLM/Keycloak/Milvus have no breaker; external outages cascade across the platform with no degraded mode. | CRITICAL | Reliability & Data Integrity | pybreaker per LiteLLM/Keycloak/Milvus with threshold + half-open recovery. | ADR-034; ADR-036
CORE-10 | No HA architecture | Every core system runs as a single copy; if any one fails, the platform goes offline with no automatic backup. | Every stateful service is single-instance (PostgreSQL/NATS/Valkey/Milvus/Keycloak/etcd) -> SPOF. | HIGH | Performance & Scalability | HA roadmap per service: Postgres streaming replication, NATS 3-node cluster, Valkey Sentinel, Milvus cluster mode, Keycloak Infinispan, etcd 3-node.
CORE-11 | No DB migration framework | We have no safe, repeatable way to upgrade the database; an upgrade could silently lose data. | Schemas created implicitly by Pydantic + MongoEngine at startup. Core upgrade may silently drop fields; no rollback or migration history. | HIGH | Reliability & Data Integrity | Versioned migration framework (Alembic-like) + metadata collection tracking applied migrations. | ADR-003 | Blocks safe SDK upgrades (see CTC-18).
CORE-12 | False docs claims | Our documentation claims privacy/compliance features that don't actually exist in the product - a credibility and audit risk. | CLAUDE.md / GDPR docs claim Presidio integration, GDPR right-to-erasure, and immutable audit logs that do not exist in code. | HIGH | Documentation / Compliance | Remove false claims from CLAUDE.md + GDPR docs; sync with reality; add doc-code drift detection CI. | ADR-017
CORE-13 | Presidio DE-only multilingual gap | The privacy filter only works for German; French / Italian / English personal data passes through unmasked. | Presidio analyzer hardcodes 'de' across 10 LiteLLM config files. Swiss FR/IT/EN data not PII-masked before reaching the LLM. | HIGH | Security | Per-language Presidio routing (DE/FR/IT/EN) + Swiss custom recognizers (AHV, CHE-UID, +41 phone). | ADR-018
CORE-14 | No mTLS service-to-service | Traffic between internal services isn't encrypted, so an attacker inside the network could eavesdrop. | NATS token-only auth; Mongo/Redis use connection strings; internal traffic not mutually authenticated -> MITM risk inside cluster. | HIGH | Security | mTLS for NATS/Mongo/Redis with automated cert rotation (cert-manager / Vault).
CORE-15 | No supply chain security (SBOM/signing/scan) | We don't scan our software components for known vulnerabilities, so we may ship insecure dependencies unknowingly. | No SBOM, image signing, or vulnerability scanning -> unknown CVEs in images, supply-chain attack risk. | HIGH | Security | syft (SBOM) + cosign (image signing) + trivy (vuln scan) in CI. | ADR-029 | Verified 2026-05-29: only Dependabot exists in CI - no SAST/SBOM/image-signing/container-scan. SBOM should be CycloneDX (OWASP) format. Process side covered by CORE-34 / adr_052.
CORE-16 | No API rate limiting | The API has no usage throttling, leaving it open to abuse, denial-of-service, and cost spikes. | API has no per-user / per-tenant rate limit -> DoS risk and cost runaway if requests reach LLM endpoints. | HIGH | Security | Redis-backed rate limiter middleware per user + per tenant.
CORE-17 | Milvus single-node memory wall | The search database can't fit large data volumes on a single machine; it will hit a hard capacity wall as data grows. | Single-node Milvus, HNSW memory wall (122 GB RAM for 10M x 3072d x 4B). | HIGH | Performance & Scalability | Milvus cluster mode + DISKANN benchmark for disk-backed index. | ADR-015
CORE-18 | No formal alerting infrastructure | There's no proper alerting / on-call system, so failures may go unnoticed until a customer complains. | Only Slack notification on Ansible Pull failure; no AlertManager, no on-call routing, no per-service severity rules. | HIGH | Observability | Prometheus AlertManager + PagerDuty/OpsGenie on-call routing + per-service severity rules. | ADR-032 | PARTIALLY MITIGATED (verified 2026-05-29): collector pipelines OTLP->SigNoz Cloud are wired, but NO alert rules as-code, no AlertManager/on-call routing in repo; SigNoz is an external Cloud (EU) sink, not self-hosted in core. Risk stands.
CORE-19 | No business metrics + formal SLI/SLO | We don't measure service quality or set targets, so we can't prove or manage reliability to customers. | No business metrics (agent_runs, HITL escalations, RAG latency); no formal SLI/SLO documented per service. | HIGH | Observability | Business metrics export; formal SLI/SLO documented per service. | ADR-010; ADR-033 | PARTIALLY MITIGATED (verified 2026-05-29): collector has traces/logs/metrics pipelines, BUT core (API/agents/pipelines/dispatcher) emits NO metrics (no MeterProvider in packages/core); only OpenWebUI/LiteLLM self-emit. Bot has no OTEL (trace breaks at bot). Host metrics/journald only via Gen 2 playbook (absent on all 5 Gen 1 customers). No SLI/SLO. Risk stands.
CORE-20 | No K8s migration path (partially addressed) | We can't easily scale beyond one server per customer yet; the new Kubernetes setup exists but isn't proven in production. | Single-server ceiling for Gen 1/Gen 2. aihub-k8s (Gen 3) exists with Terraform + Helm but no prod customer migrated; charts do NOT pin a core version. | HIGH | Operational Excellence | Adopt Gen 3 via ADR; chart-level core version pin policy; migrate >=1 prod customer; cluster-mode Milvus + HPA validation; document Gen 1 -> Gen 3 migration. | ADR-040
CORE-21 | No load test baseline | We've never load-tested the platform, so we don't know how many users / documents it can actually handle. | No load test suite or baseline numbers per critical path. | HIGH | Performance / Quality | Load test suite (k6/Locust) in CI with baseline numbers per critical path. | ADR-046
CORE-22 | Connector framework missing | Every new customer rebuilds the same data connectors from scratch, slowing onboarding and raising cost. | Every customer rebuilds source connectors (O(NxM) onboarding cost). | HIGH | SDK / Operational | BaseSourceConnector framework + built-in connectors (SMB, S3, SharePoint, Confluence, Jira, GitHub, Notion, Drive, Box, Salesforce, IMAP). | ADR-004
CORE-23 | Code RAG semantic-only (missing structural chunks) | Code-search answer quality is limited because it ignores code structure. | Code RAG uses semantic chunking only, missing structural / AST-aware chunks and symbol indexing. | HIGH | Performance / RAG | tree-sitter AST chunking + code-specific embedding (CodeBERT/UniXcoder) + hybrid index (vector + symbol + Neo4j call-graph). | ADR-044
CORE-24 | OSS dependency churn, EOL & lock-in (fast-moving AI stack) | AI tooling changes fast and we depend on many external OSS components; without continuous tracking, security / maintenance / End-of-Life issues pile up - and even open-source can lock us in via proprietary functions or protocols. | Heavy dependence on many external libraries/systems; the AI layer (parsers, embeddings, rerankers, vector stores, LLM runtimes) churns ~quarterly. As dependency volume grows, the probability that security / maintenance / EoL topics surface increases; even OSS components can cause lock-in (proprietary functions, protocols). No continuous component-health / EoL monitoring today. | HIGH | Sustainability / Architecture | Hexagonal Ports & Adapters for the 6 swappable layers + contract tests; PLUS Renovate auto-updates + End-of-Life tracking + continuous component-health monitoring (manual or automated) + an eval gate on every swap. | ADR-024; ADR-043 | Broadened 2026-05-29: now covers EoL tracking + continuous health monitoring + OSS-protocol lock-in (not just abstraction). ADR-043 is the standing strategy.
CORE-25 | Workflow architecture Process vs Agentic undecided | A whole unused module sits in the product with no decision on whether to build on it or remove it. | packages/process is dead code; strategic direction (hybrid vs deprecate) undecided. Docs still advertise process engine. | HIGH | Architecture | Option A (activate hybrid Process+Agentic with routing criteria) or Option B (deprecate process cleanly + migration guide). | ADR-013 | Marketing architecture diagram (.drawio) also depicts the process engine - remove or decide.
CORE-26 | No run / AITL timeout | Agents can run or escalate without limit, risking stuck jobs and runaway loops. | No explicit timeout per agent run; recursive AITL escalation has no depth hardcap. | HIGH | Reliability & Data Integrity | Explicit timeout per agent run + MAX_AITL_DEPTH = 5 hardcap for recursive escalation. | ADR-022
CORE-27 | Container resource limits missing in production | Services have no resource caps, so one misbehaving component can crash the entire server. | No deploy.resources.limits in docker-compose -> 1 container OOM can crash host. | HIGH | Operational / Performance | Explicit deploy.resources.limits (CPU/memory) per service; profile-based sizing.
CORE-28 | Backup encryption at rest not verified | We haven't verified backups are encrypted, so a stolen backup could expose customer data. | Restic backup encryption for off-host backup not verified; key management undocumented. | HIGH | Reliability & Data Integrity | Verify Restic encryption enabled for off-host backup; document encryption key management + rotation procedure. | ADR-030
CORE-29 | Keycloak signing key rotation procedure missing | There's no process to rotate the login signing key; if it leaks, attackers could forge logins. | No JWT signing key rotation procedure -> compromised key = unlimited token forgery. | HIGH | Security | Document JWT signing key rotation (every 6 months); automation script; audit log. | ADR-005
CORE-30 | Image vulnerability remediation SLA missing | We have no agreed timeline to patch known security vulnerabilities once they're found. | No SLA for remediating CVEs in container images (separate from scanning). | HIGH | Security | SLA for critical CVE (7 days), high (30 days), medium (90 days); track in dashboard. | ADR-029
CORE-31 | Marketing diagram advertises Meltano - not in codebase | Our marketing architecture diagram shows a data-integration engine (Meltano) that does not actually exist in the product - a credibility and audit risk. | docs/media/architecture/architecture.drawio contains 'meltano' nodes; no Meltano exists in packages/ or infra/ (pipelines are Dagster + rclone/SharePoint connectors). Review even cites Meltano only as a competitor (CORE-22). | HIGH | Documentation / Compliance | Remove Meltano from the marketing diagram or add it as a real roadmap item; extend doc-code drift detection to marketing diagrams. |  | False-claim family (ties CORE-12); related to CORE-22 connector framework gap.
CORE-32 | No accuracy/quality eval & performance benchmark process | We have no standard way to measure answer accuracy or benchmark performance, so quality problems only surface as customer complaints (e.g. FMH, WPE). | No platform-wide RAG/agent accuracy-evaluation methodology or performance-benchmark process. FMH has an unused eval framework; IGS has an ad-hoc Langfuse Citation-Quality harness; no CI quality/perf gate. Directly behind customer dissatisfaction (FMH 3.6 #12, WPE 3.5 #11). | HIGH | Quality Assurance / Performance | Standing evaluation methodology: golden datasets + LLM-as-judge metrics (relevance/correctness/citation) run in CI; performance-benchmark gate (latency/throughput) per release; promote IGS Citation-Quality + FMH eval framework to a core capability. | ADR-051; ADR-044; ADR-046 | Root NFR behind FMH-12 and WPE-11.
CORE-33 | Supported use cases not authoritatively documented | There is no official list of which AI use cases the platform supports, so sales/audit questions ('is X supported?') have no defensible answer. | Docs claim 'covers 9 of 10 enterprise AI use cases' with no ADR backing; no canonical taxonomy (Full/Partial/Out-of-scope); vision / predictive analytics / fine-tuning are out of scope but not stated (Overview 1 Weaknesses, 5 'AI use case scope undefined'). | HIGH | Documentation / Product Scope | Authoritative ADR defining the supported-use-case list with a status matrix (Full/Partial/Out-of-scope); reference it from marketing + pre-sales. | ADR-037 | Already raised in 5; now a discrete register row.
CORE-34 | No recurring security testing / DevSecOps process (SAST+DAST, pentest, threat-model, OWASP dep-check, CVSS) | Security isn't tested on a regular schedule and automated security scanning isn't defined - vulnerabilities can sit undetected. | Verified: only Dependabot in CI (no CodeQL/SAST, no DAST, no trivy/semgrep/bandit/pip-audit, no SBOM). STRIDE threat model done once with no refresh cadence; no periodic pentest; no CVSS scoring/triage; OWASP dependency-check not defined. | HIGH | Security | DevSecOps process: SAST (CodeQL/semgrep/bandit) + DAST (OWASP ZAP) in CI; OWASP dependency-check + pip-audit/trivy; CVSS-based triage + remediation SLA (ties #30); periodic pentest + scheduled threat-model refresh; SBOM in CycloneDX (ties #15). | ADR-052 | Distinct from #15 (supply-chain artifacts) and #30 (remediation SLA) - this is the testing/verification process.
CORE-35 | No defined quality attributes / NFR scenarios to drive architecture | We never defined measurable quality goals up front, so big architecture calls (like multi-tenancy) get deferred - and fixing them later forces customer-impacting data migrations. | No arc42 ch10-style quality-attribute scenarios (isolation, scalability, portability targets) agreed before architecture decisions. Concretely, multi-tenancy was deferred (CORE-03 data layer not isolated) -> a late retrofit forces tenant data migration with large customer impact (see CTC-18 tenant-schema migration, CORE-11 migration framework). | HIGH | Architecture / Governance | Define quality-attribute scenarios (arc42 ch10) as explicit architecture drivers; gate major design decisions (multi-tenancy, storage, isolation, portability) against them BEFORE build; sequence multi-tenancy + a migration framework early to avoid forced customer migrations. | ADR-053; ADR-002; ADR-003 | Multi-tenancy is the cautionary case: deferral -> forced data migration (CTC-18). Quality NFRs must drive architecture, not follow it.
CORE-36 | Insecure code execution (Jupyter) - container-only sandbox | When users run Python in the chat 'code interpreter', it executes in a SHARED container that can reach internal services and has no resource limits - closer to a plain container than a hardened sandbox, despite the 'sandbox' marketing wording. | OpenWebUI CODE_EXECUTION/INTERPRETER -> a single shared jupyter-lab (token auth, shared jupyter-data volume) on the `backend` network. Verified: no read_only / cap_drop / security_opt / pids_limit / cpu-mem limits; not isolated from backend peers (litellm holding LLM keys, otel, mineru); no per-user/tenant isolation; no egress (cannot reach internet directly, but can pivot via backend peers that have egress). | HIGH | Security | Harden: ephemeral per-session kernels (gVisor/Kata or nsjail); drop caps + read-only FS + no-new-privileges + pids/cpu/mem quotas; dedicated locked-down network (no backend-peer reach, no egress); per-user workspace; time/output limits. Correct the 'sandbox' claim. | ADR-054 | Reachable by any authenticated user holding the code-interpreter permission; 'code execution sandbox' is advertised as a strength (ties #12 false-claims).
CORE-37 | Agent permissions / bus access not scoped (no per-agent least-privilege) | Agents share one message-bus password and broad database credentials, so any agent can read every tenant's events and there is no per-agent permission boundary. | NATS uses a single shared token (authorization { token }) with NO subject-level ACL -> any agent/bot/service can publish/subscribe agent.> / process.> across ALL tenants & threads (confirms 4.0 V3). Agents also hold broad DB/S3 credentials. No per-agent least-privilege; no per-tenant tool auth (13.2); MCP tool args bypass Presidio (#5). | HIGH | Security / Multi-Tenancy | NATS per-account/per-user permissions scoped by subject incl. a tenant segment (aihub.tenant.{id}.*); least-privilege credentials per agent; per-tenant tool authorization; tie to tenant-isolation (adr_002) and Gen 3 per-tenant NATS (adr_047). | ADR-002; ADR-047 | Bus-level manifestation of the multi-tenancy gap (#3 / 4.0 V3) + agent least-privilege gap.
CORE-38 | Event bus (NATS/JetStream) not monitored | We don't monitor the message bus, so backlogs, stuck consumers, or redelivery storms go unnoticed until something breaks. | NATS exposes a monitoring endpoint (http: 8222) but it is NOT scraped into the observability backend; no prometheus-nats-exporter, no JetStream metrics (consumer lag, pending/redelivered, stream bytes), no alerts. Combined with no DLQ (#8) and no metrics/alerting (#18/#19), a poison message or stuck consumer is invisible. | HIGH | Observability / Reliability | Scrape 8222/JetStream metrics into SigNoz (prometheus-nats-exporter or OTLP); alert on consumer lag, redelivery, DLQ depth, stream storage; add dashboards. Folds into observability completeness (adr_050) + DLQ (#8). | ADR-050 | Monitoring endpoint exists but is unwired; JetStream-specific health not monitored.

## aihub-bmd
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
BMD-01 | Backup destination on the same VM | Backups sit on the same machine as the live data - if that server dies, everything is lost permanently. | FATAL: backup stored on same SeaweedFS / same VM. VM dies = total data loss. Violates 3-2-1 rule. | CRITICAL | Reliability & Data Integrity | Emergency cron sync to Swiss-sovereign off-site (Infomaniak CH / Exoscale CH / Hetzner); long-term migrate to Gen 2 (Restic->Swift). | ADR-030; ADR-031
BMD-02 | Azure OpenAI (Sweden) sovereignty violation | This customer's AI runs in Azure Sweden, breaking our Swiss-data promise. | LiteLLM config 100% Azure OpenAI (Sweden region) -> violates core sovereignty ADR 2026_02_24. | HIGH | Sovereignty & Compliance | Tied to core sovereignty path decision (Option A/B/C); ADR documenting trade-off or migration plan. | ADR-000 | Severity depends on customer compliance contract.
BMD-03 | Test coverage near-zero | Almost no automated tests, so changes can break things without warning. | Only 59 lines / 1 utility (test_snk_enrichment.py); agents and pipelines untested. | HIGH | Quality Assurance | Baseline test plan (smoke tests per agent/pipeline); integration test with staging data; coverage threshold 60% for new code.
BMD-04 | SDK drift 11 minor versions | Runs an outdated platform version and misses security fixes - but it's the easiest customer to update (quick win). | v0.279.2 vs core v0.290.4. Security patches do not propagate. | HIGH | SDK Versioning | SDK upgrade plan with security delta audit; extract reusable patterns to core; CI gate blocking drift > N versions. Near-latest pin -> lowest-risk upgrade; do first as quick win. | ADR-001; ADR-009
BMD-05 | Cohere reranking US/Canada vendor | The reranking service is a US / Canada vendor - another data-sovereignty concern. | Reranker uses Cohere (US/Canada) -> vendor + sovereignty concern. | HIGH | Sovereignty & Compliance | ADR documenting sovereignty trade-off or migrate to sovereign alternative (local BGE, local Jina). | ADR-000
BMD-06 | Storage multiplier 3.9x | Storage grows ~4x the source size; the current disk can't hold more than one customer. | ~3.9x storage multiplier (1 TB source -> 5.1 TB). 1.9 TB disk insufficient for 2+ customers. | HIGH | Performance & Scalability | Data partitioning strategy (sharding / time-based / customer-based / cold storage); ADR documenting strategy.
BMD-07 | Hardcoded customer config | Customer-specific paths are hardcoded, so the setup can't be reused for other customers without code changes. | SNK_ANCHOR, BASE_PATH (SMB share /mnt/smb_bmd/...) hardcoded in pipeline. | HIGH | Operational / Config | Pydantic Settings from env per deployment; documented config matrix. | ADR-004
BMD-08 | Weak model malformed JSON breaks workflow | A weaker AI model can produce malformed output that breaks the workflow. | Weak model can emit malformed JSON that breaks the workflow; no structured-output guard. | HIGH | Reliability / Quality | Structured output / JSON mode (response_format) + Pydantic validation + fallback chain weak->strong model + golden test suite in CI.
BMD-09 | No resource limits in docker-compose | No resource caps on services, risking a server crash from one overloaded component. | No CPU/memory limits per service. | HIGH | Operational / Performance | Explicit CPU/memory limits per service; profile-based sizing.
BMD-10 | Internal import violation | Customer code reaches into private platform internals, which will break on upgrades. | pipelines/snk_enrichment.py:2 imports core internal module (swiss_ai_hub.core.persistence.rag.vectors.node_metadata). | HIGH | SDK Versioning | Fix import via core public API (__init__.py); lint rule blocking internal imports. | ADR-038; ADR-006
BMD-11 | No own arc42 + ADRs | No architecture documentation, so knowledge lives only in developers' heads. | No architecture documentation or decision records; design lives only in code. | HIGH | Documentation | arc42 12-chapter skeleton + C4 L1/L2 + 10 ADRs (sovereignty, partitioning, SMB path, SNK enrichment, regex utils, Cohere choice, etc.).

## aihub-ctc
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
CTC-01 | Backup destination on the same Azure VM | Backups are on the same server as the data - total loss if the VM fails. | FATAL: backup on same Azure VM. VM dies = total loss. | CRITICAL | Reliability & Data Integrity | Tier 1 emergency cron sync to Swiss off-site; plan migration to Gen 2 with cross-region replication. | ADR-030; ADR-031
CTC-02 | Azure AI Foundry + Azure DI sovereignty violation | Heavy reliance on Azure AI services breaks our Swiss-sovereignty promise. | LiteLLM config 100% Azure AI Foundry (SUI+SWE) + Azure Document Intelligence -> violates core sovereignty ADR. | CRITICAL | Sovereignty & Compliance | Standardize on core stack (MinerU + LiteLLM gateway); migration roadmap DI -> MinerU, Foundry -> vLLM/Swiss LLM Cloud via LiteLLM. | ADR-000; ADR-016
CTC-03 | Per-user data access control missing | Users could see each other's documents because access isn't enforced per user - a serious data-leak / GDPR risk. | 3 manifestations, same root cause: service-account shared keys, no data-layer isolation, no ACL inheritance. Cross-user data leak. GDPR Art.32/25. | CRITICAL | Security | Per-user OAuth delegated permissions for Jira/SharePoint/Confluence; data-layer isolation (per-tenant Milvus, per-user ACL filter); ACL inheritance into Milvus; documented access matrix; forensic audit log. | ADR-020; ADR-021; ADR-002
CTC-18 | MongoDB tenant-entry schema migration required | Upgrading the platform requires a risky database migration first - the biggest upgrade blocker for this customer. | Tenant-entry schema changed between pinned and current core -> migration required before SDK upgrade. Biggest upgrade risk for CTC. | CRITICAL | Reliability / SDK | Build on DB migration framework (ADR-003); author forward + rollback migration; reconcile tenant docs vs Keycloak source of truth; dry-run on restored copy in maintenance window. | ADR-045; ADR-003
CTC-04 | Test coverage minimal | Most components have no tests, raising the risk of undetected breakage. | Only 3 files / 788 lines in log_analysis_agent; chat / jira_issue / retrieval_orchestrator agents + 6 pipelines + custom API + lib/common untested. | HIGH | Quality Assurance | Extend log_analysis_agent style coverage to all components; smoke tests per agent; integration test with staging Jira/Confluence/SharePoint; coverage threshold 60%.
CTC-05 | SDK drift 16 minor versions | Outdated platform version, missing 16 releases of fixes. | v0.274.3 vs core v0.290.4. | HIGH | SDK Versioning | SDK upgrade with security delta audit; standardize uv workflow; deprecate poetry.lock; CI gate blocking drift. | ADR-001; ADR-009
CTC-06 | SharePoint over-permissioned Sites.Read.All | The integration has tenant-wide read access to all SharePoint sites - far more than it needs. | Azure AD app-only Sites.Read.All tenant-wide -> excessive scope. | HIGH | Security | Scoped permission Sites.Selected per site; documented access matrix per site. | ADR-021 | Sub-aspect of CTC-03.
CTC-07 | Hardcoded Jira config (URL/IDs) | Jira settings are hardcoded, making the setup hard to reuse or change. | JIRA_URL, Service Desk ID, Request Type ID, Project hardcoded. | HIGH | Operational / Config | Pydantic Settings from env per deployment. | ADR-004
CTC-08 | Naming camouflage (gpt-oss-120b -> azure/gpt-5-nano) | Model names disguise that an Azure model is being used, hiding the sovereignty issue. | Model alias hides that an Azure model backs an open-source-looking name. | HIGH | Sovereignty / Transparency | Transparent naming convention (e.g., azure-eu/gpt-5-nano); ADR documenting trade-off. | ADR-000
CTC-09 | Jira webhook not idempotent | A repeated Jira event triggers duplicate work, wasting cost and creating duplicates. | JiraWebhookController: same event delivered 2x = 2 agent runs. | HIGH | Reliability & Data Integrity | Idempotency key from webhook event ID; Redis lock pattern.
CTC-10 | Custom API not yet contributed to core | Useful custom features live only in this customer's code instead of the shared platform. | Jira webhook + Support Desk endpoints live only in customer repo. | HIGH | SDK / Architecture | Extract Jira webhook + Support Desk endpoint to core as extension points; ADR decision on when to extract.
CTC-11 | External services cascade risk | An outage of Jira / SharePoint / Azure can take down this customer's service with no fallback. | Jira/Confluence/SharePoint/Azure outage cascades with no breaker/fallback. | HIGH | Reliability & Data Integrity | Circuit breaker per source; cached fallback for read paths; documented DR plan. | ADR-034
CTC-12 | Azure stack triple redundancy | Three overlapping Azure services do similar jobs, adding cost and lock-in. | Azure DI + Foundry + core MinerU+LiteLLM all present -> redundant Azure dependency. | HIGH | Sovereignty / Cost | Standardize on core stack; ADR documenting Azure-specific justification; migration roadmap. | ADR-039
CTC-13 | Azure AD B2C vendor lock-in | Identity is tied to Azure AD B2C, creating vendor lock-in. | Identity federated via Azure AD B2C instead of pure Keycloak. | HIGH | Security / Architecture | ADR documenting trade-off; evaluate pure Keycloak federation alternative.
CTC-14 | Internal import violation (lib/common/types) | Customer code uses private platform internals - fragile on upgrades. | lib/common/types/RetrievalAgentInTheLoop.py:1-4 imports non-public core module path. | HIGH | SDK Versioning | Fix import via core public API; lint rule blocking. | ADR-038; ADR-006
CTC-15 | Dual lock files | Two competing dependency files cause confusion and inconsistent builds. | poetry.lock (84KB) + uv.lock coexist -> confusion. | HIGH | SDK / Operational | Migrate to uv-only workflow; deprecate poetry.lock; standard uv commands. | ADR-001
CTC-16 | No own arc42 + ADRs | No architecture documentation or decision records. | No architecture docs or decision records. | HIGH | Documentation | arc42 12 chapters + C4 L1/L2 + 13 ADRs (Azure Foundry, DI vs MinerU, naming camouflage, service account, AD B2C, etc.).
CTC-17 | Deep-import violations in ChatAgent.py | Customer code bypasses the official platform interface, which will break on upgrade. | ChatAgent.py reaches swiss_ai_hub.core.generative_ai.{chat_history,guards} and core.i18n.locale_handler, bypassing public API. | HIGH | SDK Versioning | Refactor to import via public interface after promoting needed symbols; add ruff/lint rule blocking deep imports; CI gate. | ADR-038

## aihub-demoscope
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
DEMO-01 | SDK drift 44 minor versions | Runs a very old platform version (4+ months behind), and the exact version isn't even recorded. | v0.246.4* vs core v0.290.4 (4.5+ months behind). *SDK pin not present in pyproject.toml. | CRITICAL | SDK Versioning | Confirm actual SDK pin via deploy manifests/CI; SDK upgrade plan with security delta audit; CI gate blocking drift; coordinate breaking-change migration. | ADR-001; ADR-009
DEMO-02 | Backup destination on the same VM | Backups on the same machine as the data - total loss if it fails. | MinIO on same host as Milvus / Mongo. | CRITICAL | Reliability & Data Integrity | Emergency cron sync to Swiss off-site; replace ad-hoc backup_updater_script.py with official milvus-backup to off-host bucket; documented restore drill. | ADR-030; ADR-031
DEMO-03 | Pulumi mentioned but IaC code not committed | The documented deployment code isn't in the repo, so the setup can't be reproduced. | README claims Pulumi but no .iac/ folder in repo -> deployment irreproducible. | CRITICAL | Operational Excellence | Commit the actual Pulumi code or remove README sections; pick one IaC approach; document the real deployment process.
DEMO-12 | Agent crashes on start when upgrading the SDK | The agent crashes on startup when the platform is upgraded - a tricky upgrade ahead. | Pin is very old; agent crashes on start when upgrading SDK. | CRITICAL | SDK Versioning | Reproduce crash on staging copy; decide remediate-in-place vs rebuild on current core generation; sequence after a verified backup. | ADR-001
DEMO-13 | No backup/restore actually built | No real backup / restore exists; the customer has formally accepted the data-loss risk. | Only ad-hoc backup_updater_script.py; no token/key renewal management. Customer formally accepts responsibility. | CRITICAL | Reliability & Data Integrity | Record as customer-accepted risk (RACI) with explicit sign-off and documented data-loss exposure; provide minimal backup + key/token renewal runbook. | ADR-030
DEMO-04 | Test coverage ZERO | No tests at all. | No test_*.py, no .feature files (2 agents + 1 pipeline). | HIGH | Quality Assurance | Baseline test plan (smoke tests per agent + pipeline); BDD .feature for hash-partitioned questions flow; integration test against staging Milvus.
DEMO-05 | Manual production migration via SSH + screen + scp | Production updates are done by hand over SSH - error-prone and untraceable. | Migration done by scp + screen on the VM; progress tracked in migration_log.json on VM. | HIGH | Operational Excellence | Replace with Dagster job or k8s Job; track migration progress in DB, not a file on the VM.
DEMO-06 | Hash-partitioned Milvus design hardcoded in 3 places | The same logic is copy-pasted in 3 places; they can drift apart and cause inconsistencies. | Hash partition logic duplicated across agent + pipeline + migration script -> drift risk. | HIGH | Reliability / Architecture | Single source of truth (partition_utils.py); CI test asserting agent + pipeline + migration use the same hash function.
DEMO-07 | 4 agent variants deployed | Four near-identical agent copies run in parallel, adding operational overhead. | persona / multi_personas x public / private -> large operational surface. | HIGH | Operational Excellence | Document public/private split rationale in ADR; verify 4 instances run same code or merge into 1 binary with config flag.
DEMO-08 | Stack divergence from core (MongoDB + Redis) | Uses different databases than the standard platform, complicating support. | Uses MongoDB + Redis instead of FerretDB + Valkey. | HIGH | Architecture | ADR documenting why diverged; migration plan or accept divergence; check Mongo-specific features blocking migration.
DEMO-09 | Phoenix v10.0.4 + LiteLLM v1.77.7 (pre-Langfuse) | Outdated monitoring / LLM components missing security updates. | Pre-Langfuse observability (ADR 2026_02_10) and older LiteLLM with missing security patches. | HIGH | Observability / Security | Plan migration Phoenix -> Langfuse (ADR 2026_02_10); bump LiteLLM to current stable (v1.79+).
DEMO-10 | Mixed sovereignty | Partly Swiss-local, partly Azure - the position needs to be documented. | Azure OpenAI SUI + local vLLM (Gemma-3, gte-Qwen2, bge-reranker). | HIGH | Sovereignty & Compliance | Document partial-sovereignty position in ADR; clarify which workloads route to Azure SUI vs local vLLM; tied to core sovereignty decision. | ADR-000
DEMO-11 | No own arc42 + ADRs | No architecture documentation. | No architecture docs or decision records. | HIGH | Documentation | arc42 12 chapters + C4 L1/L2 + ADRs (stack divergence, hash partitioning, 4-variant split, sovereignty position, MinIO same-VM backup, hashed persona_id).
DEMO-14 | Vectors held in-memory | Search data is held in memory and only works because the server is oversized; it will hit a cost / scaling wall. | Works only because the box has 200 GB RAM -> cost wall as data grows. | HIGH | Performance & Scalability | Plan move to disk-backed Milvus / DISKANN before data growth; add capacity projection; run RAG/vector-design gate. | ADR-044; ADR-046

## aihub-wpe
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
WPE-01 | TLS private key committed to git | A private security key was committed to source control - it must be rotated immediately and purged from history. | wpe.ai-agents.ch+1-key.pem tracked alongside production cert; only .env is gitignored. | CRITICAL | Security | Rotate cert + key immediately (Let's Encrypt re-issue via Traefik); add *.pem, *-key.pem, secrets/ to .gitignore; rewrite git history (BFG / git filter-repo); audit who pulled the repo. | ADR-041
WPE-02 | Manual VM deployment via copy-paste | Deployment is manual copy-paste with no rollback or audit trail. | README: cp docker-compose.latest.yml /opt/docker/config/bbv/. No rollback, audit trail, or drift detection. | CRITICAL | Operational Excellence | Add minimum reproducible deploy: bash script + checksums, or migrate to Gen 2 (Ansible Pull) / Gen 3 (aihub-k8s).
WPE-03 | LLM region not in repo | We can't confirm where this customer's AI runs, so Swiss sovereignty is unverified. | Azure OpenAI base URL env-var only -> sovereignty unverified. | HIGH | Sovereignty & Compliance | Commit non-secret litellm-region.md or .env.example stating Azure region; ADR aligning with core sovereignty path. | ADR-000
WPE-04 | SDK drift 35 minor versions | Outdated platform version missing many fixes. | v0.255.6 vs core v0.290.4. | HIGH | SDK Versioning | Bump CORE_VERSION in .env.prod with security delta review; CI gate blocking drift; pin via tag, not latest fallback. | ADR-001
WPE-05 | ${CORE_VERSION:-latest} fallback to latest | If a setting is missing it silently grabs the 'latest' version - unpredictable, non-reproducible deployments. | If env var missing, falls back to latest image -> non-reproducible builds. | HIGH | Operational Excellence | Remove :-latest default - force explicit pinning; deployment must fail-fast if CORE_VERSION is unset. | ADR-040
WPE-06 | VOLUME_ROOT defaults to local relative dir | A misconfiguration could store production data in the wrong (temporary) location. | VOLUME_ROOT:-./.docker-volumes defaults to a local relative dir in production. | HIGH | Reliability / Operational | Force VOLUME_ROOT to be set (no :- fallback); document production volume root + snapshot strategy.
WPE-07 | Off-site backup not in repo | No evidence of off-site backups - possible data-loss exposure. | No evidence of Restic / Swift / cross-region sync. | HIGH | Reliability & Data Integrity | Add backup config to repo (cron + Restic to Swiss off-site); follow 3-2-1 rule; document RTO/RPO. | ADR-030; ADR-031
WPE-08 | No own arc42 + ADRs | Deployment-only repo with no design documentation. | Deployment-only repo with no design docs. | HIGH | Documentation | Minimal arc42 (context + deployment + crosscutting); ADRs for manual VM choice, identity provider, LLM region, sovereignty position.
WPE-09 | No tests of any kind | No health checks after deployment to catch a broken release. | Deployment-only repo with no smoke/health validation scripts. | HIGH | Quality Assurance | Add post-deploy smoke test (curl health endpoints, OAuth round-trip, LiteLLM ping, OpenWebUI login); fail fast on broken deploy.
WPE-10 | SigNoz Cloud EU region for OTEL | Monitoring data goes to an EU cloud region; the sovereignty implication is unclear. | Observability data leaves tenant infra; sovereignty unclear (same caveat as core). | HIGH | Observability / Sovereignty | Inherit core ADR on SigNoz region once written; document the choice locally in WPE README.
WPE-11 | Customer reports poor platform performance | Customer reports the platform is slow; root cause unknown and we're blocked waiting on them. | Root cause unknown, customer unresponsive; investigation blocked pending customer data. | HIGH | Performance & Scalability | Review Langfuse/OTEL traces + run load-test baseline (Locust) against config/hardware replica to locate bottleneck. | ADR-046 | BLOCKED pending customer input/data.
WPE-12 | Platform unused by customer (no use / no run) | The customer is not actually using or running the platform - we keep paying for hosting/maintenance with no value delivered and no production validation. | Customer engagement near zero; combined with the unresolved performance complaint (WPE-11), there is no active usage to validate upgrades or operations. | HIGH | Business / Adoption | Clarify customer intent (continue / pause / sunset) with account management; if continuing: fix WPE-11 performance blocker + onboarding push; if not: controlled decommission to stop ops cost. |  | Compounds WPE-11 (perf issue, customer unresponsive) and WPE-04 (drift 35: upgrade ROI unclear while unused).

## aihub-fmh
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
FMH-01 | SDK drift 104 minor versions | Runs by far the oldest platform version (10+ months of missing fixes) - a major, multi-step upgrade. | v0.186.0 vs core v0.290.4 - largest drift of all customers (10+ months of patches missed). | CRITICAL | SDK Versioning | Multi-step SDK upgrade plan with security delta audit (104 minors = 10+ months of patches missed); incremental upgrades v0.186 -> v0.220 -> v0.260 -> v0.290; CI gate blocking drift. If upgrade-in-place proves impractical (104 minors + LlamaIndex monkey-patch + Mongo/Redis/Phoenix divergence), evaluate REBUILDING the 3 agents from scratch on the current core generation (same remediate-vs-rebuild decision as DEMO-12). | ADR-001; ADR-009 | Upgrade to latest assessed as very complex - rebuild-from-scratch is a serious option.
FMH-02 | LlamaIndex monkey-patch for GPT-5 | A fragile workaround alters a third-party library at runtime; it will break on upgrade. | lib/common/register_openai_models.py modifies third-party globals at import time; behaviour depends on import order; drops on SDK upgrade. | CRITICAL | Architecture / Reliability | Replace with first-class core support (PR to aihub-core adding GPT-5 model registry); document workaround in ADR until removed.
FMH-03 | Azure AI Search instead of Milvus | Uses Azure search instead of our own, adding cost, lock-in, and sovereignty questions. | Stack divergence from core; vendor lock-in + double inference cost (AI Search query + LLM call). | CRITICAL | Architecture / Sovereignty | ADR justifying Azure AI Search vs core Milvus; migration plan to Milvus or formal acceptance of divergence with cost analysis. | ADR-039
FMH-04 | Backup status not in repo | No visible backup setup; we must confirm the medical data is protected. | Pulumi stores/ deploys infra but no backup workload visible. | CRITICAL | Reliability & Data Integrity | Verify Azure backup policy on Storage Account + CosmosDB/Mongo; cross-region replication for TARDOC/TARMED data; documented restore drill. | ADR-030; ADR-031
FMH-12 | Customer dissatisfied with answer quality | The customer is unhappy with answer quality because the medical data isn't structured / tested for search - needs a RAG redesign. | Structured TARDOC/TARMED data not ingested with a designed vector schema; no RAG testing/eval strategy (evaluation/ framework exists but unused). | CRITICAL | Performance / RAG | Run RAG/vector-design gate (field-aware chunking + metadata schema); wire eval harness on existing evaluation/ framework + Langfuse datasets; baseline then tune; tie to AI-Search-vs-Milvus decision. | ADR-044; ADR-039
FMH-05 | Stack divergence (MongoDB + Redis + Phoenix) | Uses older, non-standard components, complicating support and upgrades. | Pre-Langfuse stack, same as Demoscope. | HIGH | Observability / Architecture | Plan migration Phoenix -> Langfuse (ADR 2026_02_10); plan MongoDB -> FerretDB; tied to SDK upgrade.
FMH-06 | Minimal test coverage | Very thin test coverage. | 5 test_*.py + 5 BDD .feature for 3 agents + 2 pipelines. | HIGH | Quality Assurance | Coverage threshold 60% for new code; BDD features for 3-agent routing flow; integration test against TARMED test fixtures.
FMH-07 | Azure OpenAI Switzerland North + Azure AD vendor lock-in | Heavy Azure dependence - though defensible since the data is Swiss medical data. | Similar to CTC; Azure across multiple layers. | HIGH | Sovereignty / Architecture | ADR documenting Azure choice rationale (TARDOC/TARMED is Swiss-only data, so Switzerland North is defensible); evaluate Keycloak federation alternative. | ADR-000
FMH-08 | Bot uses MS Bot Framework + dev tunnel | The chatbot may depend on a developer tool in production - a stability risk. | dev/prod parity risk; prod may depend on devtunnel workflow. | HIGH | Operational Excellence | Document MS Teams integration deployment path; remove bot_emulator references from prod docs; ensure prod doesn't depend on devtunnel.
FMH-09 | Pulumi state in Azure storage account | Deployment state lives in one Azure account; losing it makes the system unrecoverable. | Single-cloud dependency; if Azure account compromised, deployment is unrecoverable. | HIGH | Operational / Reliability | Document Pulumi state account name/region in repo (not just credentials); plan state backup.
FMH-10 | No own arc42 + ADRs | No architecture documentation despite good tooling. | Has good IaC + evaluation framework but no design docs. | HIGH | Documentation | arc42 12 chapters + C4 L1/L2 + ADRs (Azure AI Search vs Milvus, GPT-5 monkey-patch, 3-agent routing, TARDOC/TARMED ingestion, MS Bot Framework choice).
FMH-11 | Hardcoded handbook namespace | A data version is hardcoded, blocking parallel snapshots and easy updates. | handbook_02_2026 hardcoded in pipeline __init__.py. | HIGH | Operational / Config | Pydantic Settings from env; allow multiple snapshots in parallel; document versioning convention (handbook_MM_YYYY). | ADR-004

## aihub-igs
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
IGS-01 | Bot ships dev fake-auth in production compose | The Teams bot can be turned into a no-login, role-spoofing endpoint by a single config value - must be removed from production. | bot service sets DANGEROUS_DEV_ONLY_AUTH_FAKE_NAME/EMAIL/OID/ROLES in docker-compose.latest.yml. | CRITICAL | Security | Gate fake-auth behind the dev stage; core hard-guard refusing it in non-dev; remove BOT_AUTH_FAKE_* from the vault; CI gate. | ADR-048 | Confirm the live pilot vault is not populating these.
IGS-02 | Core app images pinned to :latest | App images pull 'latest', so deploys aren't reproducible and version drift is unbounded. | api/web/bot/agents/pipelines use :latest; only infra images (Milvus/LiteLLM/SeaweedFS) are pinned. | HIGH | SDK / Operational | Pin an explicit CORE_VERSION tag; fail-fast if unset; CI drift gate. | ADR-040; ADR-001
IGS-03 | Sovereignty mixed / unverifiable | The LLM runs partly on Azure and partly on Swiss LLM Cloud; the actual routing isn't in the repo to confirm. | LiteLLM wired for Azure OpenAI + Swiss LLM Cloud + Cohere/Gemini/HF; litellm-config supplied by Gen 2 playbook (not tracked). | HIGH | Sovereignty & Compliance | Confirm active routing; document the (partial) sovereignty position; tie to Core sovereignty path. | ADR-000
IGS-04 | Observability drift: Phoenix vs Langfuse | The monitoring setup is contradictory between the deployment and the docs. | Compose runs Phoenix v10.0.4 (pre-Langfuse) + OTEL->SigNoz Cloud, but eval docs name Langfuse as system of record. | HIGH | Observability | Reconcile to Langfuse (ADR 2026_02_10); add it to the tracked compose/playbook; decide SigNoz-region sovereignty. | ADR-049
IGS-05 | CORS_ALLOW_ORIGIN '*' in OpenWebUI | The web app accepts requests from any origin (an explicit TODO). | OpenWebUI env CORS_ALLOW_ORIGIN: '*' with '# TODO: Make this more secure'. | HIGH | Security | Restrict CORS to known frontend origin(s); remove the wildcard before production cutover.
IGS-06 | Off-site backup not visible in repo | We can't confirm off-site backups exist for this pilot. | No backup workload in repo; expected via Gen 2 os_backups Restic->Swift role. | HIGH | Reliability & Data Integrity | Verify the Gen 2 backup role is active for IGS; document RTO/RPO and a restore drill; follow 3-2-1. | ADR-030
IGS-07 | No own arc42 + ADRs; empty README | No design documentation; the project's decisions are undocumented. | README.md is empty; no arc42 chapters or ADRs in the repo. | HIGH | Documentation | Minimal arc42 (context + deployment + crosscutting) + ADRs (Gen 2 pilot, Docling, sovereignty, Phoenix->Langfuse, latest pinning).
IGS-08 | No unit/integration tests (eval harness only) | There are no automated tests beyond an answer-quality evaluation. | Only the Langfuse eval harness (Citation Quality judge + igs_guisan dataset); no unit/integration/smoke tests. | HIGH | Quality Assurance | Add post-deploy smoke tests (health, OAuth round-trip, LiteLLM ping, OpenWebUI login); keep the eval harness.

## Gen 1 (Manual VM)
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
GEN1-01 | Backup on the same VM (no 3-2-1) | Backups live on the same machine as the data; if that server dies, everything is lost permanently. | All 5 production customers store backups on the same VM / SeaweedFS instance. Violates the 3-2-1 backup rule. | CRITICAL | Reliability & Data Integrity | Off-site backup to a Swiss-sovereign provider; long-term migrate to Gen 2 (Restic->Swift) or Gen 3. | ADR-030; ADR-031 | Affects all 5 Gen 1 customers (bmd/ctc/wpe/demoscope/fmh).
GEN1-02 | No automatic security updates | Security patches are applied by hand, so systems can stay vulnerable for a long time. | No auto-update mechanism; each VM is patched manually. Security fixes on core do not propagate. | HIGH | Security / Operational | Migrate to Gen 2 (Ansible Pull 15-min auto-reconcile) or Gen 3 (GitOps image pull).
GEN1-03 | No high availability (single VM) | Everything runs on one machine; if it fails, the customer is completely offline. | Single VM per customer, no redundancy or failover for any stateful service. | HIGH | Performance & Scalability | HA roadmap per service; move to Gen 3 for horizontal scale-out.
GEN1-04 | No rollback / drift detection / audit trail | If a deploy goes wrong there is no easy undo and no record of what changed. | Manual deploys leave no version history, no drift detection, and no audit trail. | HIGH | Operational Excellence | Reproducible, versioned deploy config; migrate to Gen 2/Gen 3.
GEN1-05 | Manual deployment (SSH / copy-paste) | Deployments are done by hand, which is error-prone and hard to reproduce. | Sysadmin SSHes in, copies a docker-compose file and runs a script by hand. | HIGH | Operational Excellence | Scripted/automated deploy with checksums; migrate to Gen 2/Gen 3.
GEN1-06 | Secrets in plain .env on the VM | Secrets sit in a plain file on the server; anyone with VM access can read them. | Credentials stored as plaintext .env on the VM filesystem. | HIGH | Security | Move to encrypted secrets (Ansible Vault in Gen 2 / K8s secrets in Gen 3).
GEN1-07 | Single-server ceiling | Cannot grow beyond one server, limiting how many users / documents a customer can have. | docker-compose on one VM; no horizontal scaling path. | HIGH | Performance & Scalability | Migrate to Gen 3 Kubernetes for horizontal scale.

## Gen 2 (Ansible Pull)
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
GEN2-01 | GitHub is a deploy single-point-of-failure | If GitHub is down, deployments and updates stop - there is no local fallback. | Ansible Pull fetches release tarball + images from GitHub/GHCR; no local mirror. | HIGH | Reliability & Data Integrity | Local mirror / registry fallback for release artifacts and images.
GEN2-02 | Same-provider backup (off-host but not off-provider) | Backups are off the server but still on the same Swiss provider; a provider or region outage could lose both copies. | Restic -> OpenStack Swift on the same Infomaniak; off-host but not off-provider. | HIGH | Reliability & Data Integrity | Cross-provider replication of backups; document RTO/RPO. | ADR-030
GEN2-03 | 3-repo version coupling, no compatibility gate | Three repos must stay compatible but nothing tests the combinations, risking broken deploys. | ops/playbook/customer repos must align; no version-compat matrix or CI gate. | HIGH | Operational / SDK | Version-compatibility matrix + CI gate across the 3 repos.
GEN2-04 | Vault password stored on the VM filesystem | The master password that unlocks all secrets sits on the VM; compromising the VM unlocks everything. | Ansible Vault (AES256) password kept on the VM filesystem. | HIGH | Security | External secret store / KMS; avoid storing the vault password on disk.
GEN2-05 | 15-min reconcile too slow for hot-fix | Urgent fixes can take up to 15 minutes to roll out automatically. | Ansible Pull reconciles every 15 minutes; no on-demand trigger. | HIGH | Operational Excellence | Add an on-demand reconcile trigger for emergency hot-fixes.
GEN2-06 | Still single-server (no HA / no scale) | Like Gen 1, still one VM per customer - no high availability or horizontal scaling. | Runtime is still docker-compose on a single VM. | HIGH | Performance & Scalability | Use Gen 3 for HA + horizontal scale.
GEN2-07 | Unproven - no production customer migrated | Gen 2 is built but no real customer runs on it yet, so it is not battle-tested. | Infrastructure ready; zero production customers migrated. | HIGH | Operational Excellence | Migrate >=1 pilot customer; document Gen 1 -> Gen 2 migration path.
GEN2-08 | SigNoz Cloud EU region for observability | Monitoring data is sent to an EU cloud region; the data-sovereignty implication is unclear. | SigNoz collector defaults to region 'eu'; SigNoz Cloud has no Swiss region. | HIGH | Observability / Sovereignty | Decide SigNoz region via ADR; consider self-hosted SigNoz for sovereignty.
GEN2-09 | Deploy-key rotation not automated | Deploy keys are rotated only 'periodically' by hand, with no automation or audit. | Deploy key rotation policy is implicit; no automation or audit log. | HIGH | Security | Automate deploy-key rotation with audit logging.

## Gen 3 (Kubernetes)
ID | Title | Summary for PO | Description | Severity | Category | Recommendation | Proposed ADR(s) | Note
GEN3-01 | Shared Milvus credential across all tenants | All tenants share one search-database login, so one tenant could read another tenant's data. | aihub-common runs Milvus standalone with a DB per tenant but a shared credential across tenants. | CRITICAL | Security / Multi-Tenancy | Per-tenant Milvus credentials + access controls. | ADR-047
GEN3-02 | No NetworkPolicy between tenant namespaces | Tenant environments can freely reach each other over the network - no isolation. | No NetworkPolicy; tenant namespaces are freely reachable from one another. | CRITICAL | Security / Multi-Tenancy | Enforce NetworkPolicy per tenant namespace. | ADR-047
GEN3-03 | Charts do not pin the core version | Deployments pull whatever image is 'latest' unless set manually, making releases unpredictable. | Helm charts use ${CORE_VERSION:-latest}; appVersion 0.1.0; no chart-level pin. | HIGH | Operational / SDK | Chart-level core version pin policy. | ADR-040
GEN3-04 | No ResourceQuota (noisy-neighbor) | One tenant can hog resources and degrade performance for the others. | No ResourceQuota per tenant namespace. | HIGH | Performance / Multi-Tenancy | ResourceQuota per tenant namespace. | ADR-047
GEN3-05 | No autoscaling (HPA); 1 replica by default | Scaling is not automatic and the default single replica limits resilience and throughput. | No HPA; 1 replica by default (only ingress=2); node pool fixed. | HIGH | Performance & Scalability | Add HPA; raise default replicas for critical services.
GEN3-06 | Shared single-instance data stores (blast radius) | Core databases are shared and single-instance, so one failure can hit all tenants at once. | Shared single-instance Postgres / FerretDB / Milvus across tenants. | HIGH | Reliability & Data Integrity | HA for shared data stores; per-tenant isolation for regulated tenants. | ADR-047
GEN3-07 | Per-tenant NATS/Redis/Neo4j single-node | Each tenant's messaging, cache and graph run as a single node with no redundancy. | Per-tenant NATS/Redis/Neo4j are single-node; NATS not clusterable as-is. | HIGH | Reliability & Data Integrity | Clusterable messaging; HA for per-tenant stateful services.
GEN3-08 | Unproven in production (test tenants only) | Only test tenants exist; no production customer has migrated, so it is not validated at scale. | Test tenants only (tenant1, jointcreate, postgres-test); HA optional. | HIGH | Operational Excellence | Migrate a pilot customer; validate HA + cluster-mode Milvus + HPA.
GEN3-09 | Semi-manual provisioning (no self-service) | Creating a tenant still needs manual steps; there is no self-service API. | Provisioning is semi-manual; no self-service tenant API. | HIGH | Operational Excellence | Tenant provisioning automation / self-service API.
GEN3-10 | Stoney Magnum: node_count not updatable | On one cloud option, cluster size can't be changed after creation, limiting scaling. | Stoney OpenStack Magnum: node_count is not updatable after cluster creation. | HIGH | Performance / Operational | Plan capacity upfront; track the upstream limitation.
GEN3-11 | Keycloak cross-namespace watch is a workaround | The identity setup relies on an unofficial community workaround, not vendor-supported behaviour. | Keycloak Operator cross-namespace-watch is a community workaround, not first-class support. | HIGH | Reliability / Operational | Track first-class Keycloak support; document risk + mitigation in ADR.